## Work Pakages
Date (Spent) | User | Activity | Work package | Project | Units
02/01/2024 | Lam Nguyen Ngoc | Management | Task #59021: Prepare next plan for phase 2 | Intranet System - GH | 3
03/01/2024 | Lam Nguyen Ngoc | Development | Task #59021: Prepare next plan for phase 2 | Intranet System - GH | 1
04/01/2024 | Lam Nguyen Ngoc | Management | Task #59021: Prepare next plan for phase 2 | Intranet System - GH | 2
04/01/2024 | Lam Nguyen Ngoc | Management | Task #59157: Prepare Closing report | Intranet System - GH | 3
09/01/2024 | Diep Tu Ngoc | Meeting | Task #59435: 9-Jan-24 Meeting Comment from demo | Intranet System - GH | 1
09/01/2024 | Lam Nguyen Ngoc | Testing | Task #59649: Demo UAT phase 1 r1 | Intranet System - GH | 2.5
10/01/2024 | Phuong Vu | Development | Task #59440: [MB] Implementing Add Button, Edit Button | Intranet System - GH | 0.25
10/01/2024 | Phuong Vu | Development | Task #59441: [MB] Modify Dashboard/Project Time Sheet | Intranet System - GH | 0.25
10/01/2024 | Ho Tran The | Development | Task #59439: [MB] Hotfix: Update Leave request screen from feedbacks | Intranet System - GH | 3.5
10/01/2024 | Phuong Vu | Development | Task #59444: [MB] Modify label, date time format | Intranet System - GH | 1
10/01/2024 | Ho Tran The | Development | Task #59449: [MB] Hotfix: Update MyTask from feedbacks | Intranet System - GH | 1
10/01/2024 | Diep Tu Ngoc | Development | Task #59488: [QC] Update database & work around | Intranet System - GH | 4
10/01/2024 | Lam Nguyen Ngoc | Management | Task #59649: Demo UAT phase 1 r1 | Intranet System - GH | 3
10/01/2024 | Lam Nguyen Ngoc | Specification | Task #59653: Prepare UAT demo data and scenatio | Intranet System - GH | 4
11/01/2024 | Phuong Vu | Development | Task #59524: [MB] Building App for demo | Intranet System - GH | 2
11/01/2024 | Phuong Vu | Development | Task #59524: [MB] Building App for demo | Intranet System - GH | 2
11/01/2024 | Lam Nguyen Ngoc | Management | Task #59649: Demo UAT phase 1 r1 | Intranet System - GH | 1.88
11/01/2024 | Lam Nguyen Ngoc | Specification | Task #59653: Prepare UAT demo data and scenatio | Intranet System - GH | 5.65
15/01/2024 | Diep Tu Ngoc | Support | Task #59488: [QC] Update database & work around | Intranet System - GH | 3
15/01/2024 | Lam Nguyen Ngoc | Development | Task #59874: Prepare backlog list and estimation | Intranet System - GH | 2
16/01/2024 | Lam Nguyen Ngoc | Internal Review | Task #59157: Prepare Closing report | Intranet System - GH | 3
22/01/2024 | Lam Nguyen Ngoc | Internal Review | Task #59157: Prepare Closing report | Intranet System - GH | 2
22/01/2024 | Lam Nguyen Ngoc | Internal Review | Task #60246: Intranet Mobile App - ISMS Audit | Intranet System - GH | 0.5
23/02/2024 | Lam Nguyen Ngoc | Other | Task #59157: Prepare Closing report | Intranet System - GH | 2
06/03/2024 | Lam Nguyen Ngoc | Development | Task #62823: Support golive App | Intranet System - GH | 8
07/03/2024 | Lam Nguyen Ngoc | Development | Task #62823: Support golive App | Intranet System - GH | 8
08/03/2024 | Diep Tu Ngoc | Testing | Task #62302: [QC][Testing] Intranet App Golive - 8-Mar-24 | Intranet System - GH | 3
08/03/2024 | Lam Nguyen Ngoc | Development | Task #62823: Support golive App | Intranet System - GH | 8
11/03/2024 | Diep Tu Ngoc | Development | Task #62339: [QC] Prepare data test | Intranet System - GH | 2
11/03/2024 | Lam Nguyen Ngoc | Development | Task #62823: Support golive App | Intranet System - GH | 8
21/03/2024 | Lam Nguyen Ngoc | Development | Task #63061: [BE] build api birthday card for MB | Intranet System - GH | 2
21/03/2024 | Lam Nguyen Ngoc | Development | Task #62823: Support golive App | Intranet System - GH | 2
21/03/2024 | Tân Nguyễn | Development | Task #63055: [MB] Show birthday greetings card dinamically | Intranet System - GH | 2
21/03/2024 | Tân Nguyễn | Development | Task #63052: [MB] Remove login using username and password | Intranet System - GH | 5
22/03/2024 | Tân Nguyễn | Development | Task #63052: [MB] Remove login using username and password | Intranet System - GH | 1
22/03/2024 | Tân Nguyễn | Development | Task #63053: [MB] Remove Mock feature | Intranet System - GH | 1
22/03/2024 | Tân Nguyễn | Development | Bug #63054: [BUG][MB] Avatar does not show properly | Intranet System - GH | 1
22/03/2024 | Lam Nguyen Ngoc | Development | Bug #63054: [BUG][MB] Avatar does not show properly | Intranet System - GH | 3